## CSF Results
| Date Conducted | Conducted By | Approved By
| 2022-12-01 | Mike Hamilton | Risk Governance Committee on 12/28/2022
Risk Assessment
Instructions: (1) Determine whether outcome can be met by existing controls (2) If not, estimate the Likelihood (i.e., opportunity + means) that the failure to meet the outcome will result in a security issue: H/M/L (3) Then estimate the Consequence (i.e., impact + criticality) that may create: H/M/L (4) Then use the product of Likelihood and Consequence to estimate risk: H/M/L (5) Finally, for each identified risk, pick 1: Accept, Avoid, Mitigate through applying additional controls, or Transfer through insurance or other risk transferrence mechanism.
Attributes key: 1 = LOW (risk), 2 = MODERATE (risk), 3 = HIGH (risk)
Cost: 1 = Internal Resource, 2 = Consultant Support, 3 = Capital Purchase
Results
The following tables present the issues and questions used to understand the presence and efficacy of current security controls, the responses obtained during reviews and interviews, and recommendations developed. Improvement: indicates completion of bodies of work and/or reduction in overall risk compared against previous years' assessment
|  |  |  | Risk Level | NIST CSF Controls
|  |  |  | Low | 85
|  |  |  | Medium | 20
|  |  |  | High | 0
|  |  |  | N/A | 3
Improvements
|  |  |  | Positive | 19
|  |  |  | Negative | 3
|  |  |  | Static | 84
|  |  |  | Risk Level | Identify
|  |  |  | Low | 25
|  |  |  | Medium | 3
|  |  |  | High | 0
|  |  |  | N/A | 1
Improvements
|  |  |  | Positive | 5
|  |  |  | Negative | 0
|  |  |  | Static | 23
|  |  |  | Risk Level | Protect
|  |  |  | Low | 27
|  |  |  | Medium | 11
|  |  |  | High | 0
|  |  |  | N/A | 1
Improvements
|  |  |  | Positive | 5
|  |  |  | Negative | 3
|  |  |  | Static | 30
|  |  |  | Risk Level | Detect
|  |  |  | Low | 13
|  |  |  | Medium | 5
|  |  |  | High | 0
|  |  |  | N/A | 0
Improvements
|  |  |  | Positive | 6
|  |  |  | Negative | 0
|  |  |  | Static | 12
|  | Mitigation Opportunities |  | Risk Level | Respond
|  | Domain | Mitigate Count | Low | 14
|  | Identify | 9 | Medium | 1
|  | Protect | 19 | High | 0
|  | Detect | 5 | N/A | 1
|  | Respond | 1 | Improvements
|  | Recover | 3 | Positive | 3
|  | Total: | 37 | Negative | 0
|  |  |  | Static | 13
|  |  |  | Risk Level | Recover
|  |  |  | Low | 6
|  |  |  | Medium | 0
|  |  |  | High | 0
|  |  |  | N/A | 0
Improvements
|  |  |  | Positive | 0
|  |  |  | Negative | 0
|  |  |  | Static | 6

## Spider Chart
Summary chart summarizing "Current" and "Goal" security posture based on the NIST Cybersecurity Framework
This chart automatically updates based on scores entered on other sheets in this workbook
Weighted Scoring Matrix
0 | Requires immediate attention - current security hazard exists and no compensating controls implemented
1 | Level 1: Initial (Being done, but falls below the threshold of minimum security effectiveness) • At this level, there are no organized processes in place demonstrated by ad hoc and informal processes; security processes are reactive and not repeatable, measurable, or scalable.
2 | Level 2: Repeatable (Being done, but needs improvement and/or changes to reach baseline security posture) • At this stage, some processes are repeatable and a formal program has been initiated to some degree, although discipline is lacking; some processes have been established, defined, and documented.
3 | Level 3: Defined (Being done, but needs improvement and/or changes to maintain baseline security posture) • Processes have been formalized, standardized, and defined to create consistency across the organization.
4 | Level 4: Managed (Processes are structured, consistent and resilient above-baseline NIST CSF security posture) • The organization is measuring, refining, and adapting their security processes to make them more effective and efficient based on the information received from their program.
5 | Level 5: Optimizing (Long-term goal: Achieve a structured, consistent and resilient best-in-class NIST CSF security posture) • Processeses are automated, documented, and constantly analyzed for optimization; cybersecurity is part of the overall culture. • Note: Reaching Level 5 does not mean that an organization’s maturity has peaked; it means that they are constantly monitoring and evolving their processes to make them better.

## Identify
Item | Outcome | Response | Likelihood | Consequence | Risk Management Technique | Risk Management Notes | Overall Risk | Cost Type | Previous Year Improvement | Maturity Level (Current) | Maturity Level (2023 Goal) | Mapping (2018)
Asset Management (ID.AM): The data, personnel, devices, systems, and facilities that enable the organization to achieve business purposes are identified and managed consistent with their relative importance to business objectives and the organization’s risk strategy
ID.AM-1 | Physical devices and systems within the organization are inventoried |  | Low Likelihood | Moderate | Accept |  | Low | Internal | Static | 2 | 3 | · CIS CSC 1 · COBIT 5 BAI09.01, BAI09.02 · ISA 62443-2-1:2009 4.2.3.4 · ISA 62443-3-3:2013 SR 7.8 · ISO/IEC 27001:2013 A.8.1.1, A.8.1.2 · NIST SP 800-53 Rev. 4 CM-8, PM-5
ID.AM-2 | Software platforms and applications within the organization are inventoried |  | Low Likelihood | Moderate | Accept | Corrective Actions: • None • Continuous improvement | Low | Internal | Static | 2 | 3 | · CIS CSC 2 · COBIT 5 BAI09.01, BAI09.02, BAI09.05 · ISA 62443-2-1:2009 4.2.3.4 · ISA 62443-3-3:2013 SR 7.8 · ISO/IEC 27001:2013 A.8.1.1, A.8.1.2, A.12.5.1 · NIST SP 800-53 Rev. 4 CM-8, PM-5
ID.AM-3 | Organizational communication and data flows are mapped |  | Low Likelihood | Minor | Mitigate |  | Low | Internal | Static | 3 | 3 | · CIS CSC 12 · COBIT 5 DSS05.02 · ISA 62443-2-1:2009 4.2.3.4 · ISO/IEC 27001:2013 A.13.2.1, A.13.2.2 · NIST SP 800-53 Rev. 4 AC-4, CA-3, CA-9, PL-8
ID.AM-4 | External information systems are catalogued |  | Low Likelihood | Moderate | Accept |  | Low | Internal | Positive | 3 | 3 | · CIS CSC 12 · COBIT 5 APO02.02, APO10.04, DSS01.02 · ISO/IEC 27001:2013 A.11.2.6 · NIST SP 800-53 Rev. 4 AC-20, SA-9
ID.AM-5 | Resources (e.g., hardware, devices, data, time, personnel, and software) are prioritized based on their classification, criticality, and business value |  | Low Likelihood | Moderate | Mitigate |  | Low | Internal | Static | 1 | 3 | · CIS CSC 13, 14 · COBIT 5 APO03.03, APO03.04, APO12.01, BAI04.02, BAI09.02 · ISA 62443-2-1:2009 4.2.3.6 · ISO/IEC 27001:2013 A.8.2.1 · NIST SP 800-53 Rev. 4 CP-2, RA-2, SA-14, SC-6
ID.AM-6 | Cyber security roles and responsibilities for the entire workforce and third-party stakeholders (e.g., suppliers, customers, partners) are established |  | Low Likelihood | Minor | Accept | Corrective Actions: None • continuous improvement | Low | Internal | Static | 3 | 3 | · CIS CSC 17, 19 · COBIT 5 APO01.02, APO07.06, APO13.01, DSS06.03 · ISA 62443-2-1:2009 4.3.2.3.3 · ISO/IEC 27001:2013 A.6.1.1 · NIST SP 800-53 Rev. 4 CP-2, PS-7, PM-11
Business Environment (ID.BE): The organization’s mission, objectives, stakeholders, and activities are understood and prioritized; this information is used to inform cyber security roles, responsibilities, and risk management decisions
ID.BE-1 | The organization’s role in the supply chain is identified and communicated |  | Low Likelihood | Minor | Accept | Corrective Actions: None | Low | Internal | Static | 3 | 3 | · COBIT 5 APO08.01, APO08.04, APO08.05, APO10.03, APO10.04, APO10.05 · ISO/IEC 27001:2013 A.15.1.1, A.15.1.2, A.15.1.3, A.15.2.1, A.15.2.2 · NIST SP 800-53 Rev. 4 CP-2, SA-12
ID.BE-2 | The organization’s place in critical infrastructure and its industry sector is identified and communicated |  | Low Likelihood | Moderate | Accept | Corrective Actions: None | Low | Internal | Static | 3 | 3 | · COBIT 5 APO02.06, APO03.01 · ISO/IEC 27001:2013 Clause 4.1 · NIST SP 800-53 Rev. 4 PM-8
ID.BE-3 | Priorities for organizational mission, objectives, and activities are established and communicated |  | Not Likely | Minor | Accept | Corrective Actions: None • Continuous Improvement - improvement in new work on mission and values | Low | Internal | Positive | 2 | 3 | · COBIT 5 APO02.01, APO02.06, APO03.01 · ISA 62443-2-1:2009 4.2.2.1, 4.2.3.6 · NIST SP 800-53 Rev. 4 PM-11, SA-14
ID.BE-4 | Dependencies and critical functions for delivery of critical services are established |  | Low Likelihood | Moderate | Mitigate |  | Low | Consultant | Static | 1 | 3 | · COBIT 5 APO10.01, BAI04.02, BAI09.02 · ISO/IEC 27001:2013 A.11.2.2, A.11.2.3, A.12.1.3 · NIST SP 800-53 Rev. 4 CP-8, PE-9, PE-11, PM-8, SA-14
ID.BE-5 | Resilience requirements to support delivery of critical services are established for all operating states (e.g. under duress/attack, during recovery, normal operations) |  | Low Likelihood | Major | Mitigate |  | Medium | Consultant | Static | 2 | 3 | · COBIT 5 BAI03.02, DSS04.02 · ISO/IEC 27001:2013 A.11.1.4, A.17.1.1, A.17.1.2, A.17.2.1 · NIST SP 800-53 Rev. 4 CP-2, CP-11, SA-13, SA-14
Governance (ID.GV): The policies, procedures, and processes to manage and monitor the organization’s regulatory, legal, risk, environmental, and operational requirements are understood and inform the management of cyber security risk
ID.GV-1 | Organizational cybersecurity policy is established and communicated |  | Not Likely | Minor | Accept | Corrective Actions: None • continuous improvement | Low | Internal | Static | 3 | 3 | · CIS CSC 19 · COBIT 5 APO01.03, APO13.01, EDM01.01, EDM01.02 · ISA 62443-2-1:2009 4.3.2.6 · ISO/IEC 27001:2013 A.5.1.1 · NIST SP 800-53 Rev. 4 -1 controls from all security control families
ID.GV-2 | Cybersecurity roles and responsibilities are coordinated and aligned with internal roles and external partners |  | Not Likely | Moderate | Accept | Corrective Actions: None • Continuous improvement | Low | Internal | Static | 2 | 3 | · CIS CSC 19 · COBIT 5 APO01.02, APO10.03, APO13.02, DSS05.04 · ISA 62443-2-1:2009 4.3.2.3.3 · ISO/IEC 27001:2013 A.6.1.1, A.7.2.1, A.15.1.1 · NIST SP 800-53 Rev. 4 PS-7, PM-1, PM-2
ID.GV-3 | Legal and regulatory requirements regarding cybersecurity, including privacy and civil liberties obligations, are understood and managed |  | Not Likely | Moderate | Accept | Corrective Actions: None • continuous improvement | Low | Internal | Static | 2 | 3 | · CIS CSC 19 · COBIT 5 BAI02.01, MEA03.01, MEA03.04 · ISA 62443-2-1:2009 4.4.3.7 · ISO/IEC 27001:2013 A.18.1.1, A.18.1.2, A.18.1.3, A.18.1.4, A.18.1.5 · NIST SP 800-53 Rev. 4 -1 controls from all security control families
ID.GV-4 | Governance and risk management processes address cybersecurity risks |  | Not Likely | Moderate | Accept | Corrective Actions: None • continuous improvement | Low | Internal | Static | 2 | 3 | · COBIT 5 EDM03.02, APO12.02, APO12.05, DSS04.02 · ISA 62443-2-1:2009 4.2.3.1, 4.2.3.3, 4.2.3.8, 4.2.3.9, 4.2.3.11, 4.3.2.4.3, 4.3.2.6.3 · ISO/IEC 27001:2013 Clause 6 · NIST SP 800-53 Rev. 4 SA-2, PM-3, PM-7, PM-9, PM-10, PM-11
Risk Assessment (ID.RA):The organization understands the cybersecurity risk to organizational operations (including mission, functions, image, or reputation), organizational assets, and individuals
ID.RA-1 | Asset vulnerabilities are identified and documented |  | Low Likelihood | Major | Accept |  | Medium | Internal | Positive | 2 | 3 | · CIS CSC 4 · COBIT 5 APO12.01, APO12.02, APO12.03, APO12.04, DSS05.01, DSS05.02 · ISA 62443-2-1:2009 4.2.3, 4.2.3.7, 4.2.3.9, 4.2.3.12 · ISO/IEC 27001:2013 A.12.6.1, A.18.2.3 · NIST SP 800-53 Rev. 4 CA-2, CA-7, CA-8, RA-3, RA-5, SA-5, SA-11, SI-2, SI-4, SI-5
ID.RA-2 | Cyber threat intelligence is received from information sharing forums and sources |  | Not Likely | Negligible | Accept |  | Low | Internal | Static | 2 | 3 | · CIS CSC 4 · COBIT 5 BAI08.01 · ISA 62443-2-1:2009 4.2.3, 4.2.3.9, 4.2.3.12 · ISO/IEC 27001:2013 A.6.1.4 · NIST SP 800-53 Rev. 4 SI-5, PM-15, PM-16
ID.RA-3 | Threats, both internal and external, are identified and documented |  | Low Likelihood | Moderate | Accept |  | Low | Internal | Static | 3 | 3 | · CIS CSC 4 · COBIT 5 APO12.01, APO12.02, APO12.03, APO12.04 · ISA 62443-2-1:2009 4.2.3, 4.2.3.9, 4.2.3.12 · ISO/IEC 27001:2013 Clause 6.1.2 · NIST SP 800-53 Rev. 4 RA-3, SI-5, PM-12, PM-16
ID.RA-4 | Potential business impacts and likelihoods are identified | This outcome is being met, as evidenced by the addition of likelihood and impact fields to this assessment against the NIST framework. | Low Likelihood | Moderate | Accept |  | Low | Internal | Static | 2 | 3 | · CIS CSC 4 · COBIT 5 DSS04.02 · ISA 62443-2-1:2009 4.2.3, 4.2.3.9, 4.2.3.12 · ISO/IEC 27001:2013 A.16.1.6, Clause 6.1.2 · NIST SP 800-53 Rev. 4 RA-2, RA-3, SA-14, PM-9, PM-11
ID.RA-5 | Threats, vulnerabilities, likelihoods, and impacts are used to determine risk | This outcome is being met. | Low Likelihood | Moderate | Accept |  | Low | Internal | Static | 2 | 3 | · CIS CSC 4 · COBIT 5 APO12.02 · ISO/IEC 27001:2013 A.12.6.1 · NIST SP 800-53 Rev. 4 RA-2, RA-3, PM-16
ID.RA-6 | Risk responses are identified and prioritized |  | Low Likelihood | Major | Accept |  | Medium | Internal | Positive | 2 | 3 | · CIS CSC 4 · COBIT 5 APO12.05, APO13.02 · ISO/IEC 27001:2013 Clause 6.1.3 · NIST SP 800-53 Rev. 4 PM-4, PM-9
Risk Management Strategy (ID.RM): The organization’s priorities, constraints, risk tolerances, and assumptions are established and used to support operational risk decisions
ID.RM-1 | Risk management processes are established, managed, and agreed to by organizational stakeholders |  | Not Likely | Minor | Accept |  | Low | Internal | Static | 2 | 3 | · CIS CSC 4 · COBIT 5 APO12.04, APO12.05, APO13.02, BAI02.03, BAI04.02 · ISA 62443-2-1:2009 4.3.4.2 · ISO/IEC 27001:2013 Clause 6.1.3, Clause 8.3, Clause 9.3 · NIST SP 800-53 Rev. 4 PM-9
ID.RM-2 | Organizational risk tolerance is determined and clearly expressed |  | Not Likely | Minor | Mitigate |  | Low | Internal | Static | 2 | 3 | · COBIT 5 APO12.06 · ISA 62443-2-1:2009 4.3.2.6.5 · ISO/IEC 27001:2013 Clause 6.1.3, Clause 8.3 · NIST SP 800-53 Rev. 4 PM-9
ID.RM-3 | The organization’s determination of risk tolerance is informed by its role in critical infrastructure and sector specific risk analysis |  | Low Likelihood | Moderate | N/A | N/A | N/A | N/A | N/A | 2 | 3 | · COBIT 5 APO12.02 · ISO/IEC 27001:2013 Clause 6.1.3, Clause 8.3 · NIST SP 800-53 Rev. 4 SA-14, PM-8, PM-9, PM-11
Risk Management Strategy (ID.SC): The organization has established and implemented the processes to identify, assess and manage supply chain risks.
ID.SC-1 | Cyber supply chain risk management processes are identified, established, assessed, managed, and agreed to by organizational stakeholders |  | Low Likelihood | Moderate | Accept |  | Low | Internal | Positive | 1 | 3 | · CIS CSC 4 · COBIT 5 APO10.01, APO10.04, APO12.04, APO12.05, APO13.02, BAI01.03, BAI02.03, BAI04.02 · ISA 62443-2-1:2009 4.3.4.2 · ISO/IEC 27001:2013 A.15.1.1, A.15.1.2, A.15.1.3, A.15.2.1, A.15.2.2 · NIST SP 800-53 Rev. 4 SA-9, SA-12, PM-9
ID.SC-2 | Suppliers and third party partners of information systems, components, and services are identified, prioritized, and assessed using a cyber supply chain risk assessment process |  | Low Likelihood | Moderate | Mitigate |  | Low | Internal | Static | 1 | 3 | · COBIT 5 APO10.01, APO10.02, APO10.04, APO10.05, APO12.01, APO12.02, APO12.03, APO12.04, APO12.05, APO12.06, APO13.02, BAI02.03 · ISA 62443-2-1:2009 4.2.3.1, 4.2.3.2, 4.2.3.3, 4.2.3.4, 4.2.3.6, 4.2.3.8, 4.2.3.9, 4.2.3.10, 4.2.3.12, 4.2.3.13, 4.2.3.14 · ISO/IEC 27001:2013 A.15.2.1, A.15.2.2 · NIST SP 800-53 Rev. 4 RA-2, RA-3, SA-12, SA-14, SA-15, PM-9
ID.SC-3 | Contracts with suppliers and third-party partners are used to implement appropriate measures designed to meet the objectives of an organization’s cybersecurity program and Cyber Supply Chain Risk Management Plan |  | Low Likelihood | Moderate | Mitigate |  | Low | Internal | Static | 2 | 3 | · COBIT 5 APO10.01, APO10.02, APO10.03, APO10.04, APO10.05 · ISA 62443-2-1:2009 4.3.2.6.4, 4.3.2.6.7 · ISO/IEC 27001:2013 A.15.1.1, A.15.1.2, A.15.1.3 · NIST SP 800-53 Rev. 4 SA-9, SA-11, SA-12, PM-9
ID.SC-4 | Suppliers and third-party partners are routinely assessed using audits, test results, or other forms of evaluations to confirm they are meeting their contractual obligations |  | Low Likelihood | Moderate | Mitigate |  | Low | Internal | Static | 1 | 3 | · COBIT 5 APO10.01, APO10.03, APO10.04, APO10.05, MEA01.01, MEA01.02, MEA01.03, MEA01.04, MEA01.05 · ISA 62443-2-1:2009 4.3.2.6.7 · ISA 62443-3-3:2013 SR 6.1 · ISO/IEC 27001:2013 A.15.2.1, A.15.2.2 · NIST SP 800-53 Rev. 4 AU-2, AU-6, AU-12, AU-16, PS-7, SA-9, SA-12
ID.SC-5 | Response and recovery planning and testing are conducted with suppliers and third-party providers |  | Not Likely | Minor | Mitigate |  | Low | Internal | Static | 1 | 3 | · CIS CSC 19, 20 · COBIT 5 DSS04.04 · ISA 62443-2-1:2009 4.3.2.5.7, 4.3.4.5.11 · ISA 62443-3-3:2013 SR 2.8, SR 3.3, SR.6.1, SR 7.3, SR 7.4 · ISO/IEC 27001:2013 A.17.1.3 · NIST SP 800-53 Rev. 4 CP-2, CP-4, IR-3, IR-4, IR-6, IR-8, IR-9

## Identify-Score
| Category | Name | Current | Goal
| Asset Management (ID.AM) Average | Asset Mgmt | 2.3333 | 3
| Business Environment (ID.BE) Average | Bus. Environment | 2.2 | 3
| Governance (ID.GV) Average | Governance | 2.25 | 3
| Risk Assessment (ID.RA) Average | Risk Assessment | 2.1667 | 3
| Risk Management Strategy (ID.RM) Average | Risk Mgmt. Strategy | 2 | 3
| Supply Chain Risk Management (ID.SC) Average | Supply Chain RM | 1.2 | 3
| Asset Management |  | Current | Goal
| ID.AM-1: Physical devices and systems within the organization are inventoried | ID.AM-1 | 2 | 3
| ID.AM-2: Software platforms and applications within the organization are inventoried | ID.AM-2 | 2 | 3
| ID.AM-3: Organizational communication and data flows are mapped | ID.AM-3 | 3 | 3
| ID.AM-4: External information systems are catalogued | ID.AM-4 | 3 | 3
| ID.AM-5: Resources (e.g., hardware, devices, data, time, and software) are prioritized based on their classification, criticality, and business value | ID.AM-5 | 1 | 3
| ID.AM-6: Cybersecurity roles and responsibilities for the entire workforce and third-party stakeholders (e.g., suppliers, customers, partners) are established | ID.AM-6 | 3 | 3
| Business Environment |  | Current | Goal
| ID.BE-1: The organization’s role in the supply chain is identified and communicated | ID.BE-1 | 3 | 3
| ID.BE-2: The organization’s place in critical infrastructure and its industry sector is identified and communicated | ID.BE-2 | 3 | 3
| ID.BE-3: Priorities for organizational mission, objectives, and activities are established and communicated | ID.BE-3 | 2 | 3
| ID.BE-4: Dependencies and critical functions for delivery of critical services are established | ID.BE-4 | 1 | 3
| ID.BE-5: Resilience requirements to support delivery of critical services are established for all operating states (e.g. under duress/attack, during recovery, normal operations) | ID.BE-5 | 2 | 3
| Governance |  | Current | Goal
| ID.GV-1: Organizational information security policy is established | ID.GV-1 | 3 | 3
| ID.GV-2: Information security roles & responsibilities are coordinated and aligned with internal roles and external partners | ID.GV-2 | 2 | 3
| ID.GV-3: Legal and regulatory requirements regarding cybersecurity, including privacy and civil liberties obligations, are understood and managed | ID.GV-3 | 2 | 3
| ID.GV-4: Governance and risk management processes address cybersecurity risks | ID.GV-4 | 2 | 3
| Risk Assessment |  | Current | Goal
| ID.RA-1: Asset vulnerabilities are identified and documented | ID.RA-1 | 2 | 3
| ID.RA-2: Cyber threat intelligence is received from information sharing forums and sources | ID.RA-2 | 2 | 3
| ID.RA-3: Threats, both internal and external, are identified and documented | ID.RA-3 | 3 | 3
| ID.RA-4: Potential business impacts and likelihoods are identified | ID.RA-4 | 2 | 3
| ID.RA-5: Threats, vulnerabilities, likelihoods, and impacts are used to determine risk | ID.RA-5 | 2 | 3
| ID.RA-6: Risk responses are identified and prioritized | ID.RA-6 | 2 | 3
| Risk Management Strategy |  | Current | Goal
| ID.RM-1: Risk management processes are established, managed, and agreed to by organizational stakeholders | ID.RM-1 | 2 | 3
| ID.RM-2: Organizational risk tolerance is determined and clearly expressed | ID.RM-2 | 2 | 3
| ID.RM-3: The organization’s determination of risk tolerance is informed by its role in critical infrastructure and sector specific risk analysis | ID.RM-3 | 2 | 3
| Supply Chain Management |  | Current | Goal
| ID.SC-1: Cyber supply chain risk management processes are identified, established, assessed, managed, and agreed to by organizational stakeholders | ID.SC-1 | 1 | 3
| ID.SC-2: Identify, prioritize and assess suppliers and third-party partners of information systems, components and services using a cyber supply chain risk assessment process | ID.SC-2 | 1 | 3
| ID.SC-3: Suppliers and 3rd-party partners are required by contract to implement appropriate measures designed to meet the objectives of the Information Security program or Cyber Supply Chain Risk Management Plan | ID.SC-3 | 2 | 3
| ID.SC-4: Suppliers and 3rd-party partners are routinely assessed to confirm that they are meeting their contractual obligations. Reviews of audits, summaries of test results, or other equivalent evaluations of suppliers/providers are conducted | ID-SC.4 | 1 | 3
| ID.SC-5: Response and recovery planning and testing are conducted with suppliers and third-party providers | ID-SC.5 | 1 | 3
Weighted Scoring Matrix
0 | Requires immediate attention - current security hazard exists and no compensating controls implemented
1 | Level 1: Initial (Being done, but falls below the threshold of minimum security effectiveness) • At this level, there are no organized processes in place demonstrated by ad hoc and informal processes; security processes are reactive and not repeatable, measurable, or scalable.
2 | Level 2: Repeatable (Being done, but needs improvement and/or changes to reach baseline security posture) • At this stage, some processes are repeatable and a formal program has been initiated to some degree, although discipline is lacking; some processes have been established, defined, and documented.
3 | Level 3: Defined (Being done, but needs improvement and/or changes to maintain baseline security posture) • Processes have been formalized, standardized, and defined to create consistency across the organization.
4 | Level 4: Managed (Processes are structured, consistent and resilient above-baseline NIST CSF security posture) • The organization is measuring, refining, and adapting their security processes to make them more effective and efficient based on the information received from their program.
5 | Level 5: Optimizing (Long-term goal: Achieve a structured, consistent and resilient best-in-class NIST CSF security posture) • Processeses are automated, documented, and constantly analyzed for optimization; cybersecurity is part of the overall culture. • Note: Reaching Level 5 does not mean that an organization’s maturity has peaked; it means that they are constantly monitoring and evolving their processes to make them better.

## Protect
Protect (organizes activities for implementing appropriate safeguards to ensure delivery of critical infrastructure services)
Item | Outcome | Response | LikeliHood | Consequence | Risk Management Technique | Risk Management Notes | Overall Risk | Cost Type | Previous Year Improvement | Maturity Level (Current) | Maturity Level (2023 Goal) | Mapping (2018)
Access Control (PR.AC): Access to assets and associated facilities is limited to authorized users, processes, or devices, and to authorized activities and transactions
PR.AC-1 | Identities and credentials are issued, managed, verified, revoked, and audited for authorized devices, users and processes |  | Low Likelihood | Major | Mitigate |  | Medium | Capital | Negative | 1 | 3 | · CIS CSC 1, 5, 15, 16 · COBIT 5 DSS05.04, DSS06.03 · ISA 62443-2-1:2009 4.3.3.5.1 · ISA 62443-3-3:2013 SR 1.1, SR 1.2, SR 1.3, SR 1.4, SR 1.5, SR 1.7, SR 1.8, SR 1.9 · ISO/IEC 27001:2013 A.9.2.1, A.9.2.2, A.9.2.3, A.9.2.4, A.9.2.6, A.9.3.1, A.9.4.2, A.9.4.3 · NIST SP 800-53 Rev. 4 AC-1, AC-2, IA-1, IA-2, IA-3, IA-4, IA-5, IA-6, IA-7, IA-8, IA-9, IA-10, IA-11
PR.AC-2 | Physical access to assets is managed and protected |  | Not Likely | Minor | Accept |  | Low | Internal | Static | 2 | 3 | · COBIT 5 DSS01.04, DSS05.05 · ISA 62443-2-1:2009 4.3.3.3.2, 4.3.3.3.8 · ISO/IEC 27001:2013 A.11.1.1, A.11.1.2, A.11.1.3, A.11.1.4, A.11.1.5, A.11.1.6, A.11.2.1, A.11.2.3, A.11.2.5, A.11.2.6, A.11.2.7, A.11.2.8 · NIST SP 800-53 Rev. 4 PE-2, PE-3, PE-4, PE-5, PE-6, PE-8
PR.AC-3 | Remote access is managed |  | Not Likely | Major | Accept |  | Medium | Internal | Static | 3 | 3 | · CIS CSC 12 · COBIT 5 APO13.01, DSS01.04, DSS05.03 · ISA 62443-2-1:2009 4.3.3.6.6 · ISA 62443-3-3:2013 SR 1.13, SR 2.6 · ISO/IEC 27001:2013 A.6.2.1, A.6.2.2, A.11.2.6, A.13.1.1, A.13.2.1 · NIST SP 800-53 Rev. 4 AC-1, AC-17, AC-19, AC-20, SC-15
PR.AC-4 | Access permissions and authorizations are managed, incorporating the principles of least privilege and separation of duties |  | Low Likelihood | Major | Mitigate |  | Medium | Capital | Static | 2 | 3 | · CIS CSC 3, 5, 12, 14, 15, 16, 18 · COBIT 5 DSS05.04 · ISA 62443-2-1:2009 4.3.3.7.3 · ISA 62443-3-3:2013 SR 2.1 · ISO/IEC 27001:2013 A.6.1.2, A.9.1.2, A.9.2.3, A.9.4.1, A.9.4.4, A.9.4.5 · NIST SP 800-53 Rev. 4 AC-1, AC-2, AC-3, AC-5, AC-6, AC-14, AC-16, AC-24
PR.AC-5 | Network integrity is protected (e.g., network segregation, network segmentation) |  | Not Likely | Moderate | Mitigate | Corrective Actions: • Apply access controls to network segments • Continue network segmentation efforts and update logical maps; Owner: CTO Compensating Controls: • No public exposure • VPN requirement • Network onitoring | Low | Internal | Static | 2 | 3 | · CIS CSC 9, 14, 15, 18 · COBIT 5 DSS01.05, DSS05.02 · ISA 62443-2-1:2009 4.3.3.4 · ISA 62443-3-3:2013 SR 3.1, SR 3.8 · ISO/IEC 27001:2013 A.13.1.1, A.13.1.3, A.13.2.1, A.14.1.2, A.14.1.3 · NIST SP 800-53 Rev. 4 AC-4, AC-10, SC-7
PR.AC-6 | Identities are proofed and bound to credentials and asserted in interactions |  | Not Likely | Minor | Accept |  | Low | Internal | Static | 3 | 3 | · CIS CSC, 16 · COBIT 5 DSS05.04, DSS05.05, DSS05.07, DSS06.03 · ISA 62443-2-1:2009 4.3.3.2.2, 4.3.3.5.2, 4.3.3.7.2, 4.3.3.7.4 · ISA 62443-3-3:2013 SR 1.1, SR 1.2, SR 1.4, SR 1.5, SR 1.9, SR 2.1 · ISO/IEC 27001:2013, A.7.1.1, A.9.2.1 · NIST SP 800-53 Rev. 4 AC-1, AC-2, AC-3, AC-16, AC-19, AC-24, IA-1, IA-2, IA-4, IA-5, IA-8, PE-2, PS-3
PR.AC-7 | Users, devices, and other assets are authenticated (e.g., single-factor, multi-factor) commensurate with the risk of the transaction (e.g., individuals’ security and privacy risks and other organizational risks) |  | Low Likelihood | Major | Mitigate |  | Medium | Capital | Static | 3 | 3 | · CIS CSC 1, 12, 15, 16 · COBIT 5 DSS05.04, DSS05.10, DSS06.10 · ISA 62443-2-1:2009 4.3.3.6.1, 4.3.3.6.2, 4.3.3.6.3, 4.3.3.6.4, 4.3.3.6.5, 4.3.3.6.6, 4.3.3.6.7, 4.3.3.6.8, 4.3.3.6.9 · ISA 62443-3-3:2013 SR 1.1, SR 1.2, SR 1.5, SR 1.7, SR 1.8, SR 1.9, SR 1.10 · ISO/IEC 27001:2013 A.9.2.1, A.9.2.4, A.9.3.1, A.9.4.2, A.9.4.3, A.18.1.4 · NIST SP 800-53 Rev. 4 AC-7, AC-8, AC-9, AC-11, AC-12, AC-14, IA-1, IA-2, IA-3, IA-4, IA-5, IA-8, IA-9, IA-10, IA-11
Awareness & Training (PR.AT): The organization’s personnel and partners are provided cybersecurity awareness education and are adequately trained to perform their information security-related duties and responsibilities consistent with related policies, procedures, and agreements.
PR.AT-1 | All users are informed and trained |  | Low Likelihood | Moderate | Accept |  | Low | Internal | Positive | 3 | 3 | · CIS CSC 17, 18 · COBIT 5 APO07.03, BAI05.07 · ISA 62443-2-1:2009 4.3.2.4.2 · ISO/IEC 27001:2013 A.7.2.2, A.12.2.1 · NIST SP 800-53 Rev. 4 AT-2, PM-13
PR.AT-2 | Privileged users understand roles & responsibilities |  | Not Likely | Moderate | Mitigate |  | Low | Internal | Static | 2 | 3 | · CIS CSC 5, 17, 18 · COBIT 5 APO07.02, DSS05.04, DSS06.03 · ISA 62443-2-1:2009 4.3.2.4.2, 4.3.2.4.3 · ISO/IEC 27001:2013 A.6.1.1, A.7.2.2 · NIST SP 800-53 Rev. 4 AT-3, PM-13
PR.AT-3 | Third-party stakeholders (e.g., suppliers, customers, partners) understand roles and responsibilities |  | Low Likelihood | Moderate | Mitigate |  | Low | Internal | Static | 2 | 3 | · CIS CSC 17 · COBIT 5 APO07.03, APO07.06, APO10.04, APO10.05 · ISA 62443-2-1:2009 4.3.2.4.2 · ISO/IEC 27001:2013 A.6.1.1, A.7.2.1, A.7.2.2 · NIST SP 800-53 Rev. 4 PS-7, SA-9, SA-16
PR.AT-4 | Senior executives understand roles & responsibilities |  | Low Likelihood | Moderate | Accept |  | Low | Internal | Static | 2 | 3 | · CIS CSC 17, 19 · COBIT 5 EDM01.01, APO01.02, APO07.03 · ISA 62443-2-1:2009 4.3.2.4.2 · ISO/IEC 27001:2013 A.6.1.1, A.7.2.2 · NIST SP 800-53 Rev. 4 AT-3, PM-13
PR.AT-5 | Physical and cybersecurity personnel understand roles & responsibilities |  | Low Likelihood | Negligible | Accept |  | Low | Internal | Static | 2 | 3 | · CIS CSC 17 · COBIT 5 APO07.03 · ISA 62443-2-1:2009 4.3.2.4.2 · ISO/IEC 27001:2013 A.6.1.1, A.7.2.2 · NIST SP 800-53 Rev. 4 AT-3, IR-2, PM-13
Data Security (PR.DS): Information and records (data) are managed consistent with the organization’s risk strategy to protect the confidentiality, integrity, and availability of information
PR.DS-1 | Data-at-rest is protected |  | Low Likelihood | Moderate | Accept |  | Low | Internal | Static | 1 | 3 | · CIS CSC 13, 14 · COBIT 5 APO01.06, BAI02.01, BAI06.01, DSS04.07, DSS05.03, DSS06.06 · ISA 62443-3-3:2013 SR 3.4, SR 4.1 · ISO/IEC 27001:2013 A.8.2.3 · NIST SP 800-53 Rev. 4 MP-8, SC-12, SC-28
PR.DS-2 | Data-in-transit is protected |  | Low Likelihood | Moderate | Mitigate |  | Low | Internal | Static | 3 | 3 | · CIS CSC 13, 14 · COBIT 5 APO01.06, DSS05.02, DSS06.06 · ISA 62443-3-3:2013 SR 3.1, SR 3.8, SR 4.1, SR 4.2 · ISO/IEC 27001:2013 A.8.2.3, A.13.1.1, A.13.2.1, A.13.2.3, A.14.1.2, A.14.1.3 · NIST SP 800-53 Rev. 4 SC-8, SC-11, SC-12
PR.DS-3 | Assets are formally managed throughout removal, transfers, and disposition |  | Low Likelihood | Minor | Accept |  | Low | Consultant | Static | 2 | 3 | · CIS CSC 1 · COBIT 5 BAI09.03 · ISA 62443-2-1:2009 4.3.3.3.9, 4.3.4.4.1 · ISA 62443-3-3:2013 SR 4.2 · ISO/IEC 27001:2013 A.8.2.3, A.8.3.1, A.8.3.2, A.8.3.3, A.11.2.5, A.11.2.7 · NIST SP 800-53 Rev. 4 CM-8, MP-6, PE-16
PR.DS-4 | Adequate capacity to ensure availability is maintained |  | Low Likelihood | Major | Mitigate |  | Medium | Internal | Static | 2 | 3 | · CIS CSC 1, 2, 13 · COBIT 5 APO13.01, BAI04.04 · ISA 62443-3-3:2013 SR 7.1, SR 7.2 · ISO/IEC 27001:2013 A.12.1.3, A.17.2.1 · NIST SP 800-53 Rev. 4 AU-4, CP-2, SC-5
PR.DS-5 | Protections against data leaks are implemented |  | Low Likelihood | Minor | Accept |  | Low | Internal | Static | 1 | 3 | · CIS CSC 13 · COBIT 5 APO01.06, DSS05.04, DSS05.07, DSS06.02 · ISA 62443-3-3:2013 SR 5.2 · ISO/IEC 27001:2013 A.6.1.2, A.7.1.1, A.7.1.2, A.7.3.1, A.8.2.2, A.8.2.3, A.9.1.1, A.9.1.2, A.9.2.3, A.9.4.1, A.9.4.4, A.9.4.5, A.10.1.1, A.11.1.4, A.11.1.5, A.11.2.1, A.13.1.1, A.13.1.3, A.13.2.1, A.13.2.3, A.13.2.4, A.14.1.2, A.14.1.3 · NIST SP 800-53 Rev. 4 AC-4, AC-5, AC-6, PE-19, PS-3, PS-6, SC-7, SC-8, SC-13, SC-31, SI-4
PR.DS-6 | Integrity checking mechanisms are used to verify software, firmware, and information integrity |  | Low Likelihood | Moderate | Mitigate |  | Low | Internal | Static | 1 | 3 | · CIS CSC 2, 3 · COBIT 5 APO01.06, BAI06.01, DSS06.02 · ISA 62443-3-3:2013 SR 3.1, SR 3.3, SR 3.4, SR 3.8 · ISO/IEC 27001:2013 A.12.2.1, A.12.5.1, A.14.1.2, A.14.1.3, A.14.2.4 · NIST SP 800-53 Rev. 4 SC-16, SI-7
PR.DS-7 | The development and testing environment(s) are separate from the production environment |  | Low Likelihood | Moderate | Mitigate |  | Low | Internal | Static | 2 | 3 | · CIS CSC 18, 20 · COBIT 5 BAI03.08, BAI07.04 · ISO/IEC 27001:2013 A.12.1.4 · NIST SP 800-53 Rev. 4 CM-2
PR.DS-8 | Integrity checking mechanisms are used to verify hardware integrity |  | Low Likelihood | Moderate | Accept |  | Low | N/A | N/A | 1 | 3 | · COBIT 5 BAI03.05 · ISA 62443-2-1:2009 4.3.4.4.4 · ISO/IEC 27001:2013 A.11.2.4 · NIST SP 800-53 Rev. 4 SA-10, SI-7
Information Protection Processes and Procedures (PR.IP): Security policies (that address purpose, scope, roles, responsibilities, and coordination among organizational entities), processes, and procedures are maintained and used to manage protection of information systems and assets
PR.IP-1 | A baseline configuration of information technology/industrial control systems is created and maintained incorporating security principles (e.g. concept of least functionality) |  | Low Likelihood | Minor | Mitigate |  | Low | Capital | Static | 1 | 3 | · CIS CSC 3, 9, 11 · COBIT 5 BAI10.01, BAI10.02, BAI10.03, BAI10.05 · ISA 62443-2-1:2009 4.3.4.3.2, 4.3.4.3.3 · ISA 62443-3-3:2013 SR 7.6 · ISO/IEC 27001:2013 A.12.1.2, A.12.5.1, A.12.6.2, A.14.2.2, A.14.2.3, A.14.2.4 · NIST SP 800-53 Rev. 4 CM-2, CM-3, CM-4, CM-5, CM-6, CM-7, CM-9, SA-10
PR.IP-2 | A System Development Life Cycle to manage systems is implemented |  | Not Likely | Minor | Mitigate |  | Low | Internal | Static | 2 | 3 | · CIS CSC 18 · COBIT 5 APO13.01, BAI03.01, BAI03.02, BAI03.03 · ISA 62443-2-1:2009 4.3.4.3.3 · ISO/IEC 27001:2013 A.6.1.5, A.14.1.1, A.14.2.1, A.14.2.5 · NIST SP 800-53 Rev. 4 PL-8, SA-3, SA-4, SA-8, SA-10, SA-11, SA-12, SA-15, SA-17, SI-12, SI-13, SI-14, SI-16, SI-17
PR.IP-3 | Configuration change control processes are in place |  | Not Likely | Moderate | Accept |  | Low | Internal | Static | 2 | 3 | · CIS CSC 3, 11 · COBIT 5 BAI01.06, BAI06.01 · ISA 62443-2-1:2009 4.3.4.3.2, 4.3.4.3.3 · ISA 62443-3-3:2013 SR 7.6 · ISO/IEC 27001:2013 A.12.1.2, A.12.5.1, A.12.6.2, A.14.2.2, A.14.2.3, A.14.2.4 · NIST SP 800-53 Rev. 4 CM-3, CM-4, SA-10
PR.IP-4 | Backups of information are conducted, maintained, and tested periodically |  | Low Likelihood | Major | Mitigate |  | Medium | Internal | Static | 1 | 3 | · CIS CSC 10 · COBIT 5 APO13.01, DSS01.01, DSS04.07 · ISA 62443-2-1:2009 4.3.4.3.9 · ISA 62443-3-3:2013 SR 7.3, SR 7.4 · ISO/IEC 27001:2013 A.12.3.1, A.17.1.2, A.17.1.3, A.18.1.3 · NIST SP 800-53 Rev. 4 CP-4, CP-6, CP-9
PR.IP-5 | Policy and regulations regarding the physical operating environment for organizational assets are met |  | Low Likelihood | Minor | Accept |  | Low | N/A | Positive | 1 | 3 | · COBIT 5 DSS01.04, DSS05.05 · ISA 62443-2-1:2009 4.3.3.3.1 4.3.3.3.2, 4.3.3.3.3, 4.3.3.3.5, 4.3.3.3.6 · ISO/IEC 27001:2013 A.11.1.4, A.11.2.1, A.11.2.2, A.11.2.3 · NIST SP 800-53 Rev. 4 PE-10, PE-12, PE-13, PE-14, PE-15, PE-18
PR.IP-6 | Data is destroyed according to policy |  | Low Likelihood | Moderate | Mitigate |  | Low | Internal | Negative | 1 | 3 | · COBIT 5 BAI09.03, DSS05.06 · ISA 62443-2-1:2009 4.3.4.4.4 · ISA 62443-3-3:2013 SR 4.2 · ISO/IEC 27001:2013 A.8.2.3, A.8.3.1, A.8.3.2, A.11.2.7 · NIST SP 800-53 Rev. 4 MP-6
PR.IP-7 | Protection processes are continuously improved |  | Not Likely | Moderate | Accept |  | Low | Internal | Static | 1 | 3 | · COBIT 5 APO11.06, APO12.06, DSS04.05 · ISA 62443-2-1:2009 4.4.3.1, 4.4.3.2, 4.4.3.3, 4.4.3.4, 4.4.3.5, 4.4.3.6, 4.4.3.7, 4.4.3.8 · ISO/IEC 27001:2013 A.16.1.6, Clause 9, Clause 10 · NIST SP 800-53 Rev. 4 CA-2, CA-7, CP-2, IR-8, PL-2, PM-6
PR.IP-8 | Effectiveness of protection technologies is shared with authorized parties |  | Not Likely | Minor | Accept |  | Low | Internal | Positive | 3 | 3 | · COBIT 5 BAI08.04, DSS03.04 · ISO/IEC 27001:2013 A.16.1.6 · NIST SP 800-53 Rev. 4 AC-21, CA-7, SI-4
PR.IP-9 | Response plans (Incident Response and Business Continuity) and recovery plans (Incident Recovery and Disaster Recovery) are in place and managed |  | Low Likelihood | Major | Mitigate |  | Medium | Internal | Negative | 2 | 3 | · CIS CSC 19 · COBIT 5 APO12.06, DSS04.03 · ISA 62443-2-1:2009 4.3.2.5.3, 4.3.4.5.1 · ISO/IEC 27001:2013 A.16.1.1, A.17.1.1, A.17.1.2, A.17.1.3 · NIST SP 800-53 Rev. 4 CP-2, CP-7, CP-12, CP-13, IR-7, IR-8, IR-9, PE-17
PR.IP-10 | Response and recovery plans are tested |  | Low Likelihood | Major | Mitigate |  | Medium | Internal | Static | 2 | 3 | · CIS CSC 19, 20 · COBIT 5 DSS04.04 · ISA 62443-2-1:2009 4.3.2.5.7, 4.3.4.5.11 · ISA 62443-3-3:2013 SR 3.3 · ISO/IEC 27001:2013 A.17.1.3 · NIST SP 800-53 Rev. 4 CP-4, IR-3, PM-14
PR.IP-11 | Cybersecurity is included in human resources practices (e.g., deprovisioning, personnel screening) |  | N/A | N/A | N/A |  | N/A | Internal | Static | 1 | 3 | · CIS CSC 5, 16 · COBIT 5 APO07.01, APO07.02, APO07.03, APO07.04, APO07.05 · ISA 62443-2-1:2009 4.3.3.2.1, 4.3.3.2.2, 4.3.3.2.3 · ISO/IEC 27001:2013 A.7.1.1, A.7.1.2, A.7.2.1, A.7.2.2, A.7.2.3, A.7.3.1, A.8.1.4 · NIST SP 800-53 Rev. 4 PS-1, PS-2, PS-3, PS-4, PS-5, PS-6, PS-7, PS-8, SA-21
PR.IP-12 | A vulnerability management plan is developed and implemented |  | Low Likelihood | Major | Accept |  | Medium | Internal | Static | 1 | 3 | · CIS CSC 4, 18, 20 · COBIT 5 BAI03.10, DSS05.01, DSS05.02 · ISO/IEC 27001:2013 A.12.6.1, A.14.2.3, A.16.1.3, A.18.2.2, A.18.2.3 · NIST SP 800-53 Rev. 4 RA-3, RA-5, SI-2
Maintenance (PR.MA): Maintenance and repairs of industrial control and information system components is performed consistent with policies and procedures
PR.MA-1 | Maintenance and repair of organizational assets is performed and logged in a timely manner, with approved and controlled tools |  | Not Likely | Negligible | Accept |  | Low | Internal | Static | 2 | 3 | · COBIT 5 BAI03.10, BAI09.02, BAI09.03, DSS01.05 · ISA 62443-2-1:2009 4.3.3.3.7 · ISO/IEC 27001:2013 A.11.1.2, A.11.2.4, A.11.2.5, A.11.2.6 · NIST SP 800-53 Rev. 4 MA-2, MA-3, MA-5, MA-6
PR.MA-2 | Remote maintenance of organizational assets is approved, logged, and performed in a manner that prevents unauthorized access |  | Not Likely | Moderate | Mitigate |  | Low | Internal | Static | 2 | 3 | · CIS CSC 3, 5 · COBIT 5 DSS05.04 · ISA 62443-2-1:2009 4.3.3.6.5, 4.3.3.6.6, 4.3.3.6.7, 4.3.3.6.8 · ISO/IEC 27001:2013 A.11.2.4, A.15.1.1, A.15.2.1 · NIST SP 800-53 Rev. 4 MA-4
Protective Technology (PR.PT): Technical security solutions are managed to ensure the security and resilience of systems and assets, consistent with related policies, procedures, and agreements
PR.PT-1 | Audit/log records are determined, documented, implemented, and reviewed in accordance with policy |  | Not Likely | Minor | Accept |  | Low | Internal | Positive | 2 | 3 | · CIS CSC 1, 3, 5, 6, 14, 15, 16 · COBIT 5 APO11.04, BAI03.05, DSS05.04, DSS05.07, MEA02.01 · ISA 62443-2-1:2009 4.3.3.3.9, 4.3.3.5.8, 4.3.4.4.7, 4.4.2.1, 4.4.2.2, 4.4.2.4 · ISA 62443-3-3:2013 SR 2.8, SR 2.9, SR 2.10, SR 2.11, SR 2.12 · ISO/IEC 27001:2013 A.12.4.1, A.12.4.2, A.12.4.3, A.12.4.4, A.12.7.1 · NIST SP 800-53 Rev. 4 AU Family
PR.PT-2 | Removable media is protected and its use is restricted according to policy |  | Low Likelihood | Moderate | Mitigate |  | Low | Capital | Static | 1 | 3 | · CIS CSC 8, 13 · COBIT 5 APO13.01, DSS05.02, DSS05.06 · ISA 62443-3-3:2013 SR 2.3 · ISO/IEC 27001:2013 A.8.2.1, A.8.2.2, A.8.2.3, A.8.3.1, A.8.3.3, A.11.2.9 · NIST SP 800-53 Rev. 4 MP-2, MP-3, MP-4, MP-5, MP-7, MP-8
PR.PT-3 | The principle of least functionality is incorporated by configuring systems to provide only essential capabilities |  | Low Likelihood | Moderate | Mitigate |  | Low | Capital | Static | 1 | 3 | · CIS CSC 3, 11, 14 · COBIT 5 DSS05.02, DSS05.05, DSS06.06 · ISA 62443-2-1:2009 4.3.3.5.1, 4.3.3.5.2, 4.3.3.5.3, 4.3.3.5.4, 4.3.3.5.5, 4.3.3.5.6, 4.3.3.5.7, 4.3.3.5.8, 4.3.3.6.1, 4.3.3.6.2, 4.3.3.6.3, 4.3.3.6.4, 4.3.3.6.5, 4.3.3.6.6, 4.3.3.6.7, 4.3.3.6.8, 4.3.3.6.9, 4.3.3.7.1, 4.3.3.7.2, 4.3.3.7.3, 4.3.3.7.4 · ISA 62443-3-3:2013 SR 1.1, SR 1.2, SR 1.3, SR 1.4, SR 1.5, SR 1.6, SR 1.7, SR 1.8, SR 1.9, SR 1.10, SR 1.11, SR 1.12, SR 1.13, SR 2.1, SR 2.2, SR 2.3, SR 2.4, SR 2.5, SR 2.6, SR 2.7 · ISO/IEC 27001:2013 A.9.1.2 · NIST SP 800-53 Rev. 4 AC-3, CM-7
PR.PT-4 | Communications and control networks are protected |  | Low Likelihood | Major | Accept |  | Medium | Internal | Static | 2 | 3 | · CIS CSC 8, 12, 15 · COBIT 5 DSS05.02, APO13.01 · ISA 62443-3-3:2013 SR 3.1, SR 3.5, SR 3.8, SR 4.1, SR 4.3, SR 5.1, SR 5.2, SR 5.3, SR 7.1, SR 7.6 · ISO/IEC 27001:2013 A.13.1.1, A.13.2.1, A.14.1.3 · NIST SP 800-53 Rev. 4 AC-4, AC-17, AC-18, CP-8, SC-7, SC-19, SC-20, SC-21, SC-22, SC-23, SC-24, SC-25, SC-29, SC-32, SC-36, SC-37, SC-38, SC-39, SC-40, SC-41, SC-43
PR.PT-5 | Mechanisms (e.g., failsafe, load balancing, hot swap) are implemented to achieve resilience requirements in normal and adverse situations |  | Not Likely | Major | Accept |  | Medium | Internal | Positive | 2 | 3 | · COBIT 5 BAI04.01, BAI04.02, BAI04.03, BAI04.04, BAI04.05, DSS01.05 · ISA 62443-2-1:2009 4.3.2.5.2 · ISA 62443-3-3:2013 SR 7.1, SR 7.2 · ISO/IEC 27001:2013 A.17.1.2, A.17.2.1 · NIST SP 800-53 Rev. 4 CP-7, CP-8, CP-11, CP-13, PL-8, SA-14, SC-6

## Protect-Score
| Category | Name | Current | Goal
| Identity Management, Authentication and Access Control (PR.AC) - Average | Identity Mgt | 2.2857 | 3
| Awareness and Training (PR.AT) - Average | Awareness and Training | 2.2 | 3
| Data Security (PR.DS) - Average | Data Security | 1.625 | 3
| Information Protection Processes and Procedures (PR.IP) - Average | Info Protection | 1.5 | 3
| Maintenance (PR.MA) - Average | Maintence | 2 | 3
| Protective Technology (PR.PT) - Average | Protective Tech | 1.6 | 3
| Identity Management |  | Current | Goal
| PR.AC-1: Identities and credentials are issued, managed, verified, revoked, and audited for authorized devices, users and processes | PR.AC-1 | 1 | 3
| PR.AC-2: Physical access to assets is managed and protected | PR.AC-2 | 2 | 3
| PR.AC-3: Remote access is managed | PR.AC-3 | 3 | 3
| PR.AC-4: Access permissions and authorizations are managed, incorporating the principles of least privilege and separation of duties | PR.AC-4 | 2 | 3
| PR.AC-5: Network integrity is protected, incorporating network segregation where appropriate | PR.AC-5 | 2 | 3
| PR.AC-6: Identities are proofed and bound to credentials, and asserted in interactions when appropriate | PR.AC-6 | 3 | 3
| PR.AC-7: Users, devices, and other assets are authenticated (e.g., single-factor, multi-factor) commensurate with the risk of the transaction (e.g., individuals’ security and privacy risks and other organizational risks) | PR.AC-7 | 3 | 3
| Awareness and Training |  | Current | Goal
| PR.AT-1: All users are informed and trained | PR.AT-1 | 3 | 3
| PR.AT-2: Privileged users understand roles and responsibilities | PR.AT-2 | 2 | 3
| PR.AT-3: Third-party stakeholders (e.g., suppliers, customers, partners) understand roles and responsibilities | PR.AT-3 | 2 | 3
| PR.AT-4: Senior executives understand roles and responsibilities | PR.AT-4 | 2 | 3
| PR.AT-5: Physical and information security personnel understand roles and responsibilities | PR.AT-5 | 2 | 3
| Data Security |  | Current | Goal
| PR.DS-1: Data-at-rest is protected | PR-DS.1 | 1 | 3
| PR.DS-2: Data-in-transit is protected | PR-DS.2 | 3 | 3
| PR.DS-3: Assets are formally managed throughout removal, transfers, and disposition | PR-DS.3 | 2 | 3
| PR.DS-4: Adequate capacity to ensure availability is maintained | PR-DS.4 | 2 | 3
| PR.DS-5: Protections against data leaks are implemented | PR-DS.5 | 1 | 3
| PR.DS-6: Integrity checking mechanisms are used to verify software, firmware, and information integrity | PR-DS.6 | 1 | 3
| PR.DS-7: The development and testing environment(s) are separate from the production environment | PR-DS.7 | 2 | 3
| PR.DS-8: Integrity checking mechanisms are used to verify hardware integrity | PR-DS.8 | 1 | 3
| Info Protection |  | Current | Goal
| PR.IP-1: A baseline configuration of information technology/industrial control systems is created and maintained incorporating appropriate security principles (e.g. concept of least functionality) | PR.IP-1 | 1 | 3
| PR.IP-2: A System Development Life Cycle to manage systems is implemented | PR.IP-2 | 2 | 3
| PR.IP-3: Configuration change control processes are in place | PR.IP-3 | 2 | 3
| PR.IP-4: Backups of information are conducted, maintained, and tested periodically | PR.IP-4 | 1 | 3
| PR.IP-5: Policy and regulations regarding the physical operating environment for organizational assets are met | PR.IP-5 | 1 | 3
| PR.IP-6: Data is destroyed according to policy | PR.IP-6 | 1 | 3
| PR.IP-7: Protection processes are continuously improved | PR.IP-7 | 1 | 3
| PR.IP-8: Effectiveness of protection technologies is shared with appropriate parties | PR.IP-8 | 3 | 3
| PR.IP-9: Response plans (Incident Response and Business Continuity) and recovery plans (Incident Recovery and Disaster Recovery) are in place and managed | PR.IP-9 | 2 | 3
| PR.IP-10: Response and recovery plans are tested | PR.IP-10 | 2 | 3
| PR.IP-11: Cybersecurity is included in human resources practices (e.g., deprovisioning, personnel screening) | PR.IP-11 | 1 | 3
| PR.IP-12: A vulnerability management plan is developed and implemented | PR.IP-12 | 1 | 3
| Maintenance |  | Current | Goal
| PR.MA-1: Maintenance and repair of organizational assets are performed and logged in a timely manner, with approved and controlled tools | PR.MA-1 | 2 | 3
| PR.MA-2: Remote maintenance of organizational assets are approved, logged, and performed in a manner that prevents unauthorized access | PR.MA-2 | 2 | 3
| Protective Tech |  | Current | Goal
| PR.PT-1: Audit/log records are determined, documented, implemented, and reviewed in accordance with policy | PR.PT-1 | 2 | 3
| PR.PT-2: Removable media is protected and its use restricted according to policy | PR.PT-2 | 1 | 3
| PR.PT-3: The principle of least functionality is incorporated by configuring systems to provide only essential capabilities | PR.PT-3 | 1 | 3
| PR.PT-4: Communications and control networks are protected | PR.PT-4 | 2 | 3
| PR.PT-5: Systems operate in pre-defined functional states to achieve availability (e.g. under duress, under attack, during recovery, normal operations) | PR.PT-5 | 2 | 3
Weighted Scoring Matrix
0 | Requires immediate attention - current security hazard exists and no compensating controls implemented
1 | Level 1: Initial (Being done, but falls below the threshold of minimum security effectiveness) • At this level, there are no organized processes in place demonstrated by ad hoc and informal processes; security processes are reactive and not repeatable, measurable, or scalable.
2 | Level 2: Repeatable (Being done, but needs improvement and/or changes to reach baseline security posture) • At this stage, some processes are repeatable and a formal program has been initiated to some degree, although discipline is lacking; some processes have been established, defined, and documented.
3 | Level 3: Defined (Being done, but needs improvement and/or changes to maintain baseline security posture) • Processes have been formalized, standardized, and defined to create consistency across the organization.
4 | Level 4: Managed (Processes are structured, consistent and resilient above-baseline NIST CSF security posture) • The organization is measuring, refining, and adapting their security processes to make them more effective and efficient based on the information received from their program.
5 | Level 5: Optimizing (Long-term goal: Achieve a structured, consistent and resilient best-in-class NIST CSF security posture) • Processeses are automated, documented, and constantly analyzed for optimization; cybersecurity is part of the overall culture. • Note: Reaching Level 5 does not mean that an organization’s maturity has peaked; it means that they are constantly monitoring and evolving their processes to make them better.

## Detect
Detect (organizes activities for identifying the occurrence of a cybersecurity event)
Item | Outcome | Response | Likelihood | Consequence | Risk Management Technique | Risk Management Notes | Overall Risk | Cost Type | Previous Year Improvement | Maturity Level (Current) | Maturity Level (2023 Goal) | Mapping (2018)
Anomalies and Events (DE.AE): Anomalous activity is detected in a timely manner and the potential impact of events is understood
DE.AE-1 | A baseline of network operations and expected data flows for users and systems is established and managed |  | Not Likely | Moderate | Accept |  | Low | Internal | Positive | 2 | 3 | · CIS CSC 1, 4, 6, 12, 13, 15, 16 · COBIT 5 DSS03.01 · ISA 62443-2-1:2009 4.4.3.3 · ISO/IEC 27001:2013 A.12.1.1, A.12.1.2, A.13.1.1, A.13.1.2 · NIST SP 800-53 Rev. 4 AC-4, CA-3, CM-2, SI-4
DE.AE-2 | Detected events are analyzed to understand attack targets and methods |  | Not Likely | Moderate | Accept |  | Low | Internal | Positive | 2 | 3 | · CIS CSC 3, 6, 13, 15 · COBIT 5 DSS05.07 · ISA 62443-2-1:2009 4.3.4.5.6, 4.3.4.5.7, 4.3.4.5.8 · ISA 62443-3-3:2013 SR 2.8, SR 2.9, SR 2.10, SR 2.11, SR 2.12, SR 3.9, SR 6.1, SR 6.2 · ISO/IEC 27001:2013 A.12.4.1, A.16.1.1, A.16.1.4 · NIST SP 800-53 Rev. 4 AU-6, CA-7, IR-4, SI-4
DE.AE-3 | Event data are aggregated and correlated from multiple sources and sensors | This outcome is being met by the SOC and MSFT monitoring. | Not Likely | Moderate | Accept |  | Low | Internal | Static | 2 | 3 | · CIS CSC 1, 3, 4, 5, 6, 7, 8, 11, 12, 13, 14, 15, 16 · COBIT 5 BAI08.02 · ISA 62443-3-3:2013 SR 6.1 · ISO/IEC 27001:2013 A.12.4.1, A.16.1.7 · NIST SP 800-53 Rev. 4 AU-6, CA-7, IR-4, IR-5, IR-8, SI-4
DE.AE-4 | Impact of events is determined | This outcome is being met by the SOC and MSFT monitoring. | Not Likely | Moderate | Accept |  | Low | Internal | Static | 2 | 3 | · CIS CSC 4, 6 · COBIT 5 APO12.06, DSS03.01 · ISO/IEC 27001:2013 A.16.1.4 · NIST SP 800-53 Rev. 4 CP-2, IR-4, RA-3, SI-4
DE.AE-5 | Incident alert thresholds are established | This outcome is being met by the SOC and MSFT monitoring. | Low Likelihood | Major | Accept |  | Medium | Internal | Static | 2 | 3 | · CIS CSC 6, 19 · COBIT 5 APO12.06, DSS03.01 · ISA 62443-2-1:2009 4.2.3.10 · ISO/IEC 27001:2013 A.16.1.4 · NIST SP 800-53 Rev. 4 IR-4, IR-5, IR-8
Security Continuous Monitoring (DE.CM): The information system and assets are monitored at discrete intervals to identify cybersecurity events and verify the effectiveness of protective measures
DE.CM-1 | The network is monitored to detect potential cybersecurity events |  | Low Likelihood | Major | Accept |  | Medium | Internal | Positive | 3 | 3 | · CIS CSC 1, 7, 8, 12, 13, 15, 16 · COBIT 5 DSS01.03, DSS03.05, DSS05.07 · ISA 62443-3-3:2013 SR 6.2 · NIST SP 800-53 Rev. 4 AC-2, AU-12, CA-7, CM-3, SC-5, SC-7, SI-4
DE.CM-2 | The physical environment is monitored to detect potential cybersecurity events |  | Low Likelihood | Moderate | Accept |  | Low | Internal | Static | 2 | 3 | · COBIT 5 DSS01.04, DSS01.05 · ISA 62443-2-1:2009 4.3.3.3.8 · ISO/IEC 27001:2013 A.11.1.1, A.11.1.2 · NIST SP 800-53 Rev. 4 CA-7, PE-3, PE-6, PE-20
DE.CM-3 | Personnel activity is monitored to detect potential cybersecurity events |  | Not Likely | Moderate | Accept |  | Low | Internal | Positive | 2 | 3 | · CIS CSC 5, 7, 14, 16 · COBIT 5 DSS05.07 · ISA 62443-3-3:2013 SR 6.2 · ISO/IEC 27001:2013 A.12.4.1, A.12.4.3 · NIST SP 800-53 Rev. 4 AC-2, AU-12, AU-13, CA-7, CM-10, CM-11
DE.CM-4 | Malicious code is detected |  | Not Likely | Major | Accept |  | Medium | Internal | Static | 2 | 3 | · CIS CSC 4, 7, 8, 12 · COBIT 5 DSS05.01 · ISA 62443-2-1:2009 4.3.4.3.8 · ISA 62443-3-3:2013 SR 3.2 · ISO/IEC 27001:2013 A.12.2.1 · NIST SP 800-53 Rev. 4 SI-3, SI-8
DE.CM-5 | Unauthorized mobile code is detected |  | Low Likelihood | Minor | Accept |  | Low | Internal | Static | 0 | 3 | · CIS CSC 7, 8 · COBIT 5 DSS05.01 · ISA 62443-3-3:2013 SR 2.4 · ISO/IEC 27001:2013 A.12.5.1, A.12.6.2 · NIST SP 800-53 Rev. 4 SC-18, SI-4, SC-44
DE.CM-6 | External service provider activity is monitored to detect potential cybersecurity events |  | Low Likelihood | Major | Mitigate |  | Low | Capital | Static | 1 | 3 | · COBIT 5 APO07.06, APO10.05 · ISO/IEC 27001:2013 A.14.2.7, A.15.2.1 · NIST SP 800-53 Rev. 4 CA-7, PS-7, SA-4, SA-9, SI-4
DE.CM-7 | Monitoring for unauthorized personnel, connections, devices, and software is performed |  | Low Likelihood | Major | Mitigate |  | Medium | Capital | Static | 1 | 3 | · CIS CSC 1, 2, 3, 5, 9, 12, 13, 15, 16 · COBIT 5 DSS05.02, DSS05.05 · ISO/IEC 27001:2013 A.12.4.1, A.14.2.7, A.15.2.1 · NIST SP 800-53 Rev. 4 AU-12, CA-7, CM-3, CM-8, PE-3, PE-6, PE-20, SI-4
DE.CM-8 | Vulnerability scans are performed |  | Low Likelihood | Major | Accept | Corrective Actions: None • Continuous improvement | Medium | Internal | Static | 2 | 3 | · CIS CSC 4, 20 · COBIT 5 BAI03.10, DSS05.01 · ISA 62443-2-1:2009 4.2.3.1, 4.2.3.7 · ISO/IEC 27001:2013 A.12.6.1 · NIST SP 800-53 Rev. 4 RA-5
Detection Process (DE.DP): Detection processes and procedures are maintained and tested to ensure timely and adequate awareness of anomalous events
DE.DP-1 | Roles and responsibilities for detection are well defined to ensure accountability |  | Not Likely | Moderate | Mitigate |  | Low | Internal | Static | 2 | 3 | · CIS CSC 19 · COBIT 5 APO01.02, DSS05.01, DSS06.03 · ISA 62443-2-1:2009 4.4.3.1 · ISO/IEC 27001:2013 A.6.1.1, A.7.2.2 · NIST SP 800-53 Rev. 4 CA-2, CA-7, PM-14
DE.DP-2 | Detection activities comply with all applicable requirements |  | Not Likely | Moderate | N/A |  | Low | Internal | Positive | 3 | 3 | · COBIT 5 DSS06.01, MEA03.03, MEA03.04 · ISA 62443-2-1:2009 4.4.3.2 · ISO/IEC 27001:2013 A.18.1.4, A.18.2.2, A.18.2.3 · NIST SP 800-53 Rev. 4 AC-25, CA-2, CA-7, SA-18, SI-4, PM-14
DE.DP-3 | Detection processes are tested |  | Not Likely | Moderate | Mitigate |  | Low | Internal | Static | 2 | 3 | · COBIT 5 APO13.02, DSS05.02 · ISA 62443-2-1:2009 4.4.3.2 · ISA 62443-3-3:2013 SR 3.3 · ISO/IEC 27001:2013 A.14.2.8 · NIST SP 800-53 Rev. 4 CA-2, CA-7, PE-3, SI-3, SI-4, PM-14
DE.DP-4 | Event detection information is communicated to authorized parties |  | Not Likely | Moderate | Accept |  | Low | Internal | Static | 3 | 3 | · CIS CSC 19 · COBIT 5 APO08.04, APO12.06, DSS02.05 · ISA 62443-2-1:2009 4.3.4.5.9 · ISA 62443-3-3:2013 SR 6.1 · ISO/IEC 27001:2013 A.16.1.2, A.16.1.3 · NIST SP 800-53 Rev. 4 AU-6, CA-2, CA-7, RA-5, SI-4
DE.DP-5 | Detection processes are continuously improved |  | Not Likely | Moderate | Mitigate |  | Low | Internal | Positive | 3 | 3 | · COBIT 5 APO11.06, APO12.06, DSS04.05 · ISA 62443-2-1:2009 4.4.3.4 · ISO/IEC 27001:2013 A.16.1.6 · NIST SP 800-53 Rev. 4, CA-2, CA-7, PL-2, RA-5, SI-4, PM-14

## Detect-Score
| Category | Name | Current | Goal
| Anomalies and Events (DE.AE) - Average | Anomalies and Events | 2 | 3
| Security Continuous Monitoring (DE.CM) - Average | Continuous Monitoring | 1.625 | 3
| Detection Processes (DE.DP) - Average | Detection Processes | 2.6 | 3
| Anomalies and Events |  | Current | Goal
| DE.AE-1: A baseline of network operations and expected data flows for users and systems is established and managed | DE.AE-1 | 2 | 3
| DE.AE-2: Detected events are analyzed to understand attack targets and methods | DE.AE-2 | 2 | 3
| DE.AE-3: Event data are collected and correlated from multiple sources and sensors | DE.AE-3 | 2 | 3
| DE.AE-4: Impact of events is determined | DE.AE-4 | 2 | 3
| DE.AE-5: Incident alert thresholds are established | DE.AE-5 | 2 | 3
| Continous Monitoring |  | Current | Goal
| DE.CM-1: The network is monitored to detect potential cybersecurity events | DE.CM-1 | 3 | 3
| DE.CM-2: The physical environment is monitored to detect potential cybersecurity events | DE.CM-2 | 2 | 3
| DE.CM-3: Personnel activity is monitored to detect potential cybersecurity events | DE.CM-3 | 2 | 3
| DE.CM-4: Malicious code is detected | DE.CM-4 | 2 | 3
| DE.CM-5: Unauthorized mobile code is detected | DE.CM-5 | 0 | 3
| DE.CM-6: External service provider activity is monitored to detect potential cybersecurity events | DE.CM-6 | 1 | 3
| DE.CM-7: Monitoring for unauthorized personnel, connections, devices, and software is performed | DE.CM-7 | 1 | 3
| DE.CM-8: Vulnerability scans are performed | DE.CM-8 | 2 | 3
| Detection Process |  | Current | Goal
| DE.DP-1: Roles and responsibilities for detection are well defined to ensure accountability | DE.DP-1 | 2 | 3
| DE.DP-2: Detection activities comply with all applicable requirements | DE.DP-2 | 3 | 3
| DE.DP-3: Detection processes are tested | DE.DP-3 | 2 | 3
| DE.DP-4: Event detection information is communicated to appropriate parties | DE.DP-4 | 3 | 3
| DE.DP-5: Detection processes are continuously improved | DE.DP-5 | 3 | 3
Weighted Scoring Matrix
0 | Requires immediate attention - current security hazard exists and no compensating controls implemented
1 | Level 1: Initial (Being done, but falls below the threshold of minimum security effectiveness) • At this level, there are no organized processes in place demonstrated by ad hoc and informal processes; security processes are reactive and not repeatable, measurable, or scalable.
2 | Level 2: Repeatable (Being done, but needs improvement and/or changes to reach baseline security posture) • At this stage, some processes are repeatable and a formal program has been initiated to some degree, although discipline is lacking; some processes have been established, defined, and documented.
3 | Level 3: Defined (Being done, but needs improvement and/or changes to maintain baseline security posture) • Processes have been formalized, standardized, and defined to create consistency across the organization.
4 | Level 4: Managed (Processes are structured, consistent and resilient above-baseline NIST CSF security posture) • The organization is measuring, refining, and adapting their security processes to make them more effective and efficient based on the information received from their program.
5 | Level 5: Optimizing (Long-term goal: Achieve a structured, consistent and resilient best-in-class NIST CSF security posture) • Processeses are automated, documented, and constantly analyzed for optimization; cybersecurity is part of the overall culture. • Note: Reaching Level 5 does not mean that an organization’s maturity has peaked; it means that they are constantly monitoring and evolving their processes to make them better.

## Respond
Respond (organizes activities for taking action regarding a detected cybersecurity event)
Item | Outcome | Response | Likelihood | Consequence | Risk Management Technique | Risk Management Notes | Overall Risk | Cost Type | Previous Year Improvement | Maturity Level (Current) | Maturity Level (2023 Goal) | Mapping (2018)
Response Planning (RS.RP): Response processes and procedures are executed and maintained, to ensure timely response to detected cybersecurity events
RS.RP-1 | Response plan is executed during or after an event |  | Not Likely | Moderate | Mitigate |  | Low | Internal | Positive | 3 | 3 | · CIS CSC 19 · COBIT 5 APO12.06, BAI01.10 · ISA 62443-2-1:2009 4.3.4.5.1 · ISO/IEC 27001:2013 A.16.1.5 · NIST SP 800-53 Rev. 4 CP-2, CP-10, IR-4, IR-8
Communications (RS.CO): Response activities are coordinated with internal and external stakeholders, as appropriate, to include external support from law enforcement
RS.CO-1 | Personnel know their roles and order of operations when a response is needed |  | Not Likely | Moderate | Accept |  | Low | Internal | Static | 3 | 3 | · CIS CSC 19 · COBIT 5 EDM03.02, APO01.02, APO12.03 · ISA 62443-2-1:2009 4.3.4.5.2, 4.3.4.5.3, 4.3.4.5.4 · ISO/IEC 27001:2013 A.6.1.1, A.7.2.2, A.16.1.1 · NIST SP 800-53 Rev. 4 CP-2, CP-3, IR-3, IR-8
RS.CO-2 | Incidents are reported consistent with established criteria |  | Not Likely | Minor | N/A |  | Low | Internal | Static | 3 | 3 | · CIS CSC 19 · COBIT 5 DSS01.03 · ISA 62443-2-1:2009 4.3.4.5.5 · ISO/IEC 27001:2013 A.6.1.3, A.16.1.2 · NIST SP 800-53 Rev. 4 AU-6, IR-6, IR-8
RS.CO-3 | Information is shared consistent with response plans |  | Not Likely | Minor | N/A |  | Low | Internal | Static | 3 | 3 | · CIS CSC 19 · COBIT 5 DSS03.04 · ISA 62443-2-1:2009 4.3.4.5.2 · ISO/IEC 27001:2013 A.16.1.2, Clause 7.4, Clause 16.1.2 · NIST SP 800-53 Rev. 4 CA-2, CA-7, CP-2, IR-4, IR-8, PE-6, RA-5, SI-4
RS.CO-4 | Coordination with stakeholders occurs consistent with response plans |  | Not Likely | Minor | N/A |  | Low | Internal | Static | 3 | 3 | · CIS CSC 19 · COBIT 5 DSS03.04 · ISA 62443-2-1:2009 4.3.4.5.5 · ISO/IEC 27001:2013 Clause 7.4 · NIST SP 800-53 Rev. 4 CP-2, IR-4, IR-8
RS.CO-5 | Voluntary information sharing occurs with external stakeholders to achieve broader cybersecurity situational awareness |  | Not Likely | Negligible | Accept |  | N/A | Internal | Static | 1 | 3 | · CIS CSC 19 · COBIT 5 BAI08.04 · ISO/IEC 27001:2013 A.6.1.4 · NIST SP 800-53 Rev. 4 SI-5, PM-15
Analysis (RS.AN): Analysis is conducted to ensure adequate response and support recover activities
RS.AN-1 | Notifications from detection systems are investigated |  | Low Likelihood | Moderate | Accept |  | Low | Internal | Static | 3 | 3 | · CIS CSC 4, 6, 8, 19 · COBIT 5 DSS02.04, DSS02.07 · ISA 62443-2-1:2009 4.3.4.5.6, 4.3.4.5.7, 4.3.4.5.8 · ISA 62443-3-3:2013 SR 6.1 · ISO/IEC 27001:2013 A.12.4.1, A.12.4.3, A.16.1.5 · NIST SP 800-53 Rev. 4 AU-6, CA-7, IR-4, IR-5, PE-6, SI-4
RS.AN-2 | The impact of the incident is understood |  | Low Likelihood | Moderate | Accept |  | Low | Internal | Static | 3 | 3 | · COBIT 5 DSS02.02 · ISA 62443-2-1:2009 4.3.4.5.6, 4.3.4.5.7, 4.3.4.5.8 · ISO/IEC 27001:2013 A.16.1.4, A.16.1.6 · NIST SP 800-53 Rev. 4 CP-2, IR-4
RS.AN-3 | Forensics are performed |  | Low Likelihood | Moderate | Accept | Corrective Actions:None • Continuous improvement | Low | Internal | Static | 2 | 3 | · COBIT 5 APO12.06, DSS03.02, DSS05.07 · ISA 62443-3-3:2013 SR 2.8, SR 2.9, SR 2.10, SR 2.11, SR 2.12, SR 3.9, SR 6.1 · ISO/IEC 27001:2013 A.16.1.7 · NIST SP 800-53 Rev. 4 AU-7, IR-4
RS.AN-4 | Incidents are categorized consistent with response plans |  | Not Likely | Negligible | N/A | Corrective Actions:None • Continuous improvement | Low | Internal | Static | 2 | 3 | · CIS CSC 19 · COBIT 5 DSS02.02 · ISA 62443-2-1:2009 4.3.4.5.6 · ISO/IEC 27001:2013 A.16.1.4 · NIST SP 800-53 Rev. 4 CP-2, IR-4, IR-5, IR-8
RS.AN-5 | Processes are established to receive, analyze and respond to vulnerabilities disclosed to the organization from internal and external sources (e.g. internal testing, security bulletins, or security researchers) |  | Not Likely | Moderate | Accept | Corrective Actions: None • Continuous improvement | Low | Internal | Positive | 2 | 3 | · CIS CSC 4, 19 · COBIT 5 EDM03.02, DSS05.07 · NIST SP 800-53 Rev. 4 SI-5, PM-15
Mitigation (RS.MI): Activities are performed to prevent expansion of an event, mitigate its effects, and eradicate the incident
RS.MI-1 | Incidents are contained |  | Not Likely | Catastrophic | Transfer |  | Medium | Internal | Static | 3 | 3 | · CIS CSC 19 · COBIT 5 APO12.06 · ISA 62443-2-1:2009 4.3.4.5.6 · ISA 62443-3-3:2013 SR 5.1, SR 5.2, SR 5.4 · ISO/IEC 27001:2013 A.12.2.1, A.16.1.5 · NIST SP 800-53 Rev. 4 IR-4
RS.MI-2 | Incidents are mitigated | This outcome is being met. | Not Likely | Major | Transfer |  | Low | Internal | Static | 3 | 3 | · CIS CSC 4, 19 · COBIT 5 APO12.06 · ISA 62443-2-1:2009 4.3.4.5.6, 4.3.4.5.10 · ISO/IEC 27001:2013 A.12.2.1, A.16.1.5 · NIST SP 800-53 Rev. 4 IR-4
RS.MI-3 | Newly identified vulnerabilities are mitigated or documented as accepted risks |  | Not Likely | Major | Accept |  | Low | Internal | Positive | 2 | 3 | · CIS CSC 4 · COBIT 5 APO12.06 · ISO/IEC 27001:2013 A.12.6.1 · NIST SP 800-53 Rev. 4 CA-7, RA-3, RA-5
Improvements (RS.IM): Organizational response activities are improved by incorporating lessons learned from current and previous detection/response activities
RS.IM-1 | Response plans incorporate lessons learned |  | Not Likely | Minor | Accept |  | Low | Internal | Static | 3 | 3 | · COBIT 5 BAI01.13 · ISA 62443-2-1:2009 4.3.4.5.10, 4.4.3.4 · ISO/IEC 27001:2013 A.16.1.6, Clause 10 · NIST SP 800-53 Rev. 4 CP-2, IR-4, IR-8
RS.IM-2 | Response strategies are updated |  | Not Likely | Minor | Accept |  | Low | Internal | Static | 3 | 3 | · COBIT 5 BAI01.13, DSS04.08 · ISO/IEC 27001:2013 A.16.1.6, Clause 10 · NIST SP 800-53 Rev. 4 CP-2, IR-4, IR-8

## Respond-Score
| Category | Name | Current | Goal
| Response Planning (RS.RP) - Average | Response Planning | 3 | 3
| Communications (RS.CO) - Average | Communications | 2.6 | 3
| Analysis (RS.AN) - Average | Analysis | 2.4 | 3
| Mitigation (RS.MI) - Average | Mitigation | 2.6667 | 3
| Improvements (RS.IM) - Average | Improvements | 3 | 3
| Response Planning |  | Current | Goal
| RS.RP-1: Response plan is executed during or after an incident | RS.RP-1 | 3 | 3
| Communications |  | Current | Goal
| RS.CO-1: Personnel know their roles and order of operations when a response is needed | RS.CO-1 | 3 | 3
| RS.CO-2: Incidents are reported consistent with established criteria | RS.CO-2 | 3 | 3
| RS.CO-3: Information is shared consistent with response plans | RS.CO-3 | 3 | 3
| RS.CO-4: Coordination with stakeholders occurs consistent with response plans | RS.CO-4 | 3 | 3
| RS.CO-5: Voluntary information sharing occurs with external stakeholders to achieve broader cybersecurity situational awareness | RS.CO-5 | 1 | 3
| Analysis |  | Current | Goal
| RS.AN-1: Notifications from detection systems are investigated | RS.AN-1 | 3 | 3
| RS.AN-2: The impact of the incident is understood | RS.AN-2 | 3 | 3
| RS.AN-3: Forensics are performed | RS.AN-3 | 2 | 3
| RS.AN-4: Incidents are categorized consistent with response plans | RS.AN-4 | 2 | 3
| RS.AN-5: Processes are established to receive, analyze and respond to vulnerabilities disclosed to the organization from internal and external sources (e.g. internal testing, security bulletins, or security researchers) | RS.AN-5 | 2 | 3
| Mitigation |  | Current | Goal
| RS.MI-1: Incidents are contained | RS.MI-1 | 3 | 3
| RS.MI-2: Incidents are mitigated | RS.MI-2 | 3 | 3
| RS.MI-3: Newly identified vulnerabilities are mitigated or documented as accepted risks | RS.MI-3 | 2 | 3
| Improvements |  | Current | Goal
| RS.IM-1: Response plans incorporate lessons learned | RS.IM-1 | 3 | 3
| RS.IM-2: Response strategies are updated | RS.IM-2 | 3 | 3
Weighted Scoring Matrix
0 | Requires immediate attention - current security hazard exists and no compensating controls implemented
1 | Level 1: Initial (Being done, but falls below the threshold of minimum security effectiveness) • At this level, there are no organized processes in place demonstrated by ad hoc and informal processes; security processes are reactive and not repeatable, measurable, or scalable.
2 | Level 2: Repeatable (Being done, but needs improvement and/or changes to reach baseline security posture) • At this stage, some processes are repeatable and a formal program has been initiated to some degree, although discipline is lacking; some processes have been established, defined, and documented.
3 | Level 3: Defined (Being done, but needs improvement and/or changes to maintain baseline security posture) • Processes have been formalized, standardized, and defined to create consistency across the organization.
4 | Level 4: Managed (Processes are structured, consistent and resilient above-baseline NIST CSF security posture) • The organization is measuring, refining, and adapting their security processes to make them more effective and efficient based on the information received from their program.
5 | Level 5: Optimizing (Long-term goal: Achieve a structured, consistent and resilient best-in-class NIST CSF security posture) • Processeses are automated, documented, and constantly analyzed for optimization; cybersecurity is part of the overall culture. • Note: Reaching Level 5 does not mean that an organization’s maturity has peaked; it means that they are constantly monitoring and evolving their processes to make them better.

## Recover
Recover (organizes activities for maintaining plans for resilience and restoring any capabilities or services impaired due to a cybersecurity event.)
Item | Outcome | Response | Likelihood | Consequence | Risk Management Technique | Risk Management Notes | Overall Risk | Cost Type | Previous Year Improvement | Maturity Level (Current) | Maturity Level (2023 Goal) | Mapping (2018)
Recovery Planning (RC.RP): Recovery processes and procedures are executed and maintained to ensure timely restoration of systems or assets affected by cybersecurity events.
RC.RP-1 | Recovery plan is executed during or after an event |  | Low Likelihood | Moderate | Mitigate |  | Low | Internal | Static | 1 | 3 | · CIS CSC 10 · COBIT 5 APO12.06, DSS02.05, DSS03.04 · ISO/IEC 27001:2013 A.16.1.5 · NIST SP 800-53 Rev. 4 CP-10, IR-4, IR-8
Improvements (RC.IM):Recovery planning and processes are improved by incorporating lessons learned into future activities
RC.IM-1 | Recovery plans incorporate lessons learned |  | Low Likelihood | Minor | Mitigate |  | Low | Internal | Static | 1 | 3 | · COBIT 5 APO12.06, BAI05.07, DSS04.08 · ISA 62443-2-1:2009 4.4.3.4 · ISO/IEC 27001:2013 A.16.1.6, Clause 10 · NIST SP 800-53 Rev. 4 CP-2, IR-4, IR-8
RC.IM-2 | Recovery strategies are updated |  | Low Likelihood | Minor | Mitigate |  | Low | Internal | Static | 1 | 3 | · COBIT 5 APO12.06, BAI07.08 · ISO/IEC 27001:2013 A.16.1.6, Clause 10 · NIST SP 800-53 Rev. 4 CP-2, IR-4, IR-8
Communications (RC.CO): Restoration activities are coordinated with internal and external parties, such as coordinating centers, Internet Service Providers, owners of attacking systems, victims, other CSIRTs, and vendors
RC.CO-1 | Public relations are managed |  | Low Likelihood | Major | Accept |  | Low | Internal | Static | 3 | 3 | · COBIT 5 EDM03.02 · ISO/IEC 27001:2013 A.6.1.4, Clause 7.4
RC.CO-2 | Reputation after an event is repaired |  | Low Likelihood | Major | Transfer |  | Low | Internal | Static | 3 | 3 | · COBIT 5 MEA03.02 · ISO/IEC 27001:2013 Clause 7.4
RC.CO-3 | Recovery activities are communicated to internal and external stakeholders as well as executive and management teams |  | Low Likelihood | Minor | Accept |  | Low | Internal | Static | 3 | 3 | · COBIT 5 APO12.06 · ISO/IEC 27001:2013 Clause 7.4 · NIST SP 800-53 Rev. 4 CP-2, IR-4

## Recover-Score
| Category | Name | Current | Goal
| Recovery Planning (RC.RP) - Average | Recovery Planning | 1 | 3
| Improvements (RC.IM) - Average | Improvements | 1 | 3
| Communications (RC.CO) - Average | Communications | 3 | 3
Recover: Self-scoring worksheet (note: enter an "as is" and "to be" score, from 0 to 5, in column D and E for all of the cells that are shaded light green)
| Recovery Planning |  | Current | Goal
| RC.RP-1: Recovery plan is executed during or after a cybersecurity incident | RC.RP-1 | 1 | 3
| Improvements |  | Current | Goal
| RC.IM-1: Recovery plans incorporate lessons learned | RC.IM-1 | 1 | 3
| RC.IM-2: Recovery strategies are updated | RC.IM-2 | 1 | 3
| Communications |  | Current | Goal
| RC.CO-1: Public relations are managed | RC.CO-1 | 3 | 3
| RC.CO-2: Reputation after an event is repaired | RC.CO-2 | 3 | 3
| RC.CO-3: Recovery activities are communicated to internal stakeholders and executive and management teams | RC.CO-3 | 3 | 3
Weighted Scoring Matrix
0 | Requires immediate attention - current security hazard exists and no compensating controls implemented
1 | Level 1: Initial (Being done, but falls below the threshold of minimum security effectiveness) • At this level, there are no organized processes in place demonstrated by ad hoc and informal processes; security processes are reactive and not repeatable, measurable, or scalable.
2 | Level 2: Repeatable (Being done, but needs improvement and/or changes to reach baseline security posture) • At this stage, some processes are repeatable and a formal program has been initiated to some degree, although discipline is lacking; some processes have been established, defined, and documented.
3 | Level 3: Defined (Being done, but needs improvement and/or changes to maintain baseline security posture) • Processes have been formalized, standardized, and defined to create consistency across the organization.
4 | Level 4: Managed (Processes are structured, consistent and resilient above-baseline NIST CSF security posture) • The organization is measuring, refining, and adapting their security processes to make them more effective and efficient based on the information received from their program.
5 | Level 5: Optimizing (Long-term goal: Achieve a structured, consistent and resilient best-in-class NIST CSF security posture) • Processeses are automated, documented, and constantly analyzed for optimization; cybersecurity is part of the overall culture. • Note: Reaching Level 5 does not mean that an organization’s maturity has peaked; it means that they are constantly monitoring and evolving their processes to make them better.

## Roadmap (hidden)
Corrective Action Roadmap
Within 6 Months | Internal Resource Hours | Professional Services Estimated Cost | Estimated Capital Cost
High risk corrective actions, or indexed on most appropriate attribute(s) | 20 |  | 15000 | Risk Level | Risk Count - NIST CSF Controls + Tactical Findings
Totals: | 20 | 0 | 15000
Within 1 Year | Internal Resource Hours | Professional Services Estimated Cost | Estimated Capital Cost
Medium risk corrective actions, or indexed on most appropriate attribute(s) | 160 | 20000 | 60000
Totals | 160 | 20000 | 60000
Within 2 Years
Perform an inventory of physical devices on the network, including IoT, and document the results in an artifact to be refreshed at least annually. | 320
Totals | 320 | 0 | 0

## Program Costs (hidden)
Estimated program management costs, annual
Programmatic task | Internal Resource Hours | Professional Services
Routine meetings, ad-hoc incident management, consulting project management, planning, recordkeeping | 416 |  | Information Security Governance and Management Framework
Access authorization review | 64 |  | Weekly | Monthly | Quarterly | Annually
Reporting to security governance committee | 32 |  | Meetings (change control, infosec, governance, etc.) | Review vulnerability assessment results, assign disposition and delegate | Access authorization management reviews | Penetration test
Firewall rules and other routine inspections: | 50 |  | Incident Management | Firewall rules review | Conduct Security Governance Committee meeting | Risk Assessment
Conducting rituals for vulnerability remediation and addressing corrective actions | 100 |  | Consulting project management | Recordkeeping (e.g. security testing results for products in use) | Perform 2 of the annual requirements | Security Awareness Training / Attestation
Risk Assessment: | 40 |  | Planning for upcoming monthly, quarterly or annual requirements | Corrective action board; infosec ritual | Report to Executive Security Governance Committee | Tabletop or functional security exercise
Tabletop exercise: | 40 |  |  |  | Conduct Vulnerability Assessment | Policy review
Policy review: | 40 |  |  |  |  | Service audits
Penetration test |  | 22000 |  |  |  | Participate in annual planning and budget development
Awareness training |  | 15000
Risk Assessment |  | 15000
Annual cost estimate | 782 | 52000

## Analytics Roll-up (hidden)
| Current | Goal | Q1 | Q2 | Q3 | Q4
Identify
Asset Mgmt | 2.3333 | 3
Bus. Environment | 2.2 | 3
Governance | 2.25 | 3
Risk Assessment | 2.1667 | 3
Risk Mgmt. Strategy | 2 | 3
Supply Chain RM | 1.2 | 3
Protect
Identity Mgt | 2.2857 | 3
Awareness and Training | 2.2 | 3
Data Security | 1.625 | 3
Info Protection | 1.5 | 3
Maintence | 2 | 3
Protective Tech | 1.6 | 3
Detect
Anomalies and Events | 2 | 3
Continuous Monitoring | 1.625 | 3
Detection Processes | 2.6 | 3
Respond
Response Planning | 3 | 3
Communications | 2.6 | 3
Analysis | 2.4 | 3
Mitigation | 2.6667 | 3
Improvements | 3 | 3
Recover
Recovery Planning | 1 | 3
Improvements | 1 | 3
Communications | 3 | 3
Identify

## Matrix Codes
| Likelihood Risk Factor Matrix | [7 empty] | Likelihood Determination |  |  |  |  | Likelihood List
| Opportunity | [7 empty] | Level | Likelihood | Probability of Occurrence |  |  | N/A
| Means |  | O-1 | O-2 | O-3 | O-4 | O-5 |  | 1 | Not Likely | ~10% | May occur in exceptional circumstances |  | Not Likely
|  | M-5 | 2 | 3 | 5 | 5 | 5 |  | 2 | Low Likelihood | ~30% | Might occur on occasion |  | Low Likelihood
|  | M-4 | 2 | 3 | 4 | 5 | 5 |  | 3 | Likely | ~50% | Could occur under most circumstances |  | Likely
|  | M-3 | 1 | 2 | 3 | 4 | 5 |  | 4 | Highly Likely | ~70% | Will probably occur |  | Highly Likely
|  | M-2 | 1 | 2 | 3 | 4 | 4 |  | 5 | Near Certainty | ~90% | Expected under most circumstances |  | Near Certainty
|  | M-1 | 1 | 1 | 2 | 3 | 4
| Means: Represents an estimation of an adversary's difficulty in creating the conditions necessary for a risk occurrence. | [7 empty] | Opportunity: Represents an estimation of an adversary's accessibility to exploit a system. A system's attack surface is the set of methods or interfaces through which an adversary can enter the system and conduct an attack. Opportunity is an estimation of a system's attack surface.
| Consequence Risk Factor Matrix | [7 empty] | Consequence Determination |  |  |  |  | Consequence List
| Criticality | [12 empty] | N/A
| Impact |  | C-1 | C-2 | C-3 | C-4 | C-5 |  | Level | Consequence |  |  |  | Negligible
|  | I-5 | 2 | 3 | 4 | 5 | 5 |  | 1 | Negligible | Few perceivable changes in operations |  |  | Minor
|  | I-4 | 2 | 3 | 4 | 4 | 5 |  | 2 | Minor | Operations affected, work-around possible |  |  | Moderate
|  | I-3 | 1 | 2 | 3 | 4 | 5 |  | 3 | Moderate | Decreased network operations |  |  | Major
|  | I-2 | 1 | 1 | 2 | 3 | 4 |  | 4 | Major | Significant decrease or impact to operations |  |  | Catastrophic
|  | I-1 | 1 | 1 | 1 | 2 | 3 |  | 5 | Catastrophic | Widespread network failure without alternative
| Impact: Represents an estimation of the effect or consequence that may result from an attack on the system resulting in a specific risk occurrence. | [7 empty] | Criticality: Represents an estimation of the change in the system performance and the relationship of this change on dependent systems.
Risk Management Strategy
[11 empty] | Cost |  | Weighted Codes | N/A
|  |  | Overall Risk Factor Matrix | [7 empty] | N/A |  | N/A | Accept
[5 empty] | Consequence | [5 empty] | Internal |  | 0 | Avoid
[5 empty] | 1 | 2 | 3 | 4 | 5 |  | Consultant |  | 1 | Mitigate
|  |  | Likelihood | 5 | Low | Moderate | High | High | High |  | Capital |  | 2 | Transfer
|  |  |  | 4 | Low | Moderate | Moderate | High | High |  |  |  | 3
|  |  |  | 3 | Low | Low | Moderate | High | High |  | Previous Year Improvement |  | 4 | Overall Risk
|  |  |  | 2 | Low | Low | Low | Moderate | Moderate |  | Positive |  | 5 | N/A
|  |  |  | 1 | Low | Low | Low | Low | Moderate |  | Negative |  |  | Low
[11 empty] | Static |  |  | Medium
[11 empty] | N/A |  |  | High
Weighted Scoring Matrix
0 | Requires immediate attention - current security hazard exists and no compensating controls implemented
1 | Level 1: Initial (Being done, but falls below the threshold of minimum security effectiveness) • At this level, there are no organized processes in place demonstrated by ad hoc and informal processes; security processes are reactive and not repeatable, measurable, or scalable.
2 | Level 2: Repeatable (Being done, but needs improvement and/or changes to reach baseline security posture) • At this stage, some processes are repeatable and a formal program has been initiated to some degree, although discipline is lacking; some processes have been established, defined, and documented.
3 | Level 3: Defined (Being done, but needs improvement and/or changes to maintain baseline security posture) • Processes have been formalized, standardized, and defined to create consistency across the organization.
4 | Level 4: Managed (Processes are structured, consistent and resilient above-baseline NIST CSF security posture) • The organization is measuring, refining, and adapting their security processes to make them more effective and efficient based on the information received from their program.
5 | Level 5: Optimizing (Long-term goal: Achieve a structured, consistent and resilient best-in-class NIST CSF security posture) • Processes are automated, documented, and constantly analyzed for optimization; cybersecurity is part of the overall culture. • Note: Reaching Level 5 does not mean that an organization’s maturity has peaked; it means that they are constantly monitoring and evolving their processes to make them better.